## Cover Page
Task Management Tracker
Get 10% OFF our course using coupon code EMAIL10
Get our Excel for Business & Finance Course
Go to Data Here
Made by Career Principles Ltd.
Note
All content is copyright material of Career Principles Ltd.
This Excel model may not be reproduced or distributed by any means, including printing, screencapturing, or any other method without the prior permission of the publisher.

## Dashboard
Task ID | Task Name | Team | Task Owner | Start Date | Due Date | Task Duration | Status | Overdue? | Comments
T001 | Prepare Q4 Financial Report | Finance | Sarah Johnson | 2025-09-02 | 2025-09-20 | 18 | Completed | FALSE | Submitted to CFO for review.
T002 | Conduct Market Research | Strategy | Sarah Johnson | 2025-09-05 | 2025-09-25 | 20 | Completed | FALSE | Draft findings ready; awaiting survey data.
T003 | Redesign Website Homepage | Strategy | David Kim | 2025-07-10 | 2025-08-05 | 26 | In Progress | TRUE | Wireframes approved; development in progress.
T004 | Update Sales Forecast for FY2026 | Finance | Sarah Johnson | 2025-09-12 | 2025-09-30 | 18 | Completed | FALSE | Final version shared with Sales Director.
T005 | Implement CRM Upgrade | Strategy | James Miller | 2025-09-15 | 2025-10-10 | 25 | In Progress | TRUE | Vendor confirmed delivery timeline.
T006 | Plan Annual Company Retreat | HR | David Kim | 2025-09-18 | 2025-10-15 | 27 | In Progress | TRUE | Venue options being shortlisted.
T007 | Review Legal for Contracts | HR | Alex Chen | 2025-08-20 | 2025-08-27 | 7 | Not Started | TRUE | Updated contracts aligned with new regulation.
T008 | Launch Social Media Campaign | Marketing | Alex Chen | 2025-09-22 | 2025-10-12 | 20 | In Progress | TRUE | Initial creatives approved, campaign scheduled.
T009 | Recruit New Data Analyst | HR | Sarah Johnson | 2025-09-23 | 2025-10-20 | 27 | Completed | FALSE | First round of interviews completed.
T010 | Conduct Employee Survey | HR | Sarah Johnson | 2025-09-24 | 2025-10-05 | 11 | In Progress | TRUE | Survey questions finalized.
T011 | Prepare Investor Presentation | Finance | David Kim | 2025-09-25 | 2025-10-02 | 7 | Completed | FALSE | Draft slides ready; awaiting financial highlights.
T012 | Upgrade Infrastructure | Strategy | Sarah Johnson | 2025-09-26 | 2025-10-30 | 34 | Completed | FALSE | External consultant engagement pending.
T013 | Evaluate Vendor Proposals for Logistics | Strategy | Emily Davis | 2025-09-27 | 2025-10-07 | 10 | In Progress | TRUE | Three proposals shortlisted for management review.
T014 | Draft Q1 Marketing Strategy | Strategy | Emily Davis | 2025-09-28 | 2025-10-18 | 20 | Completed | FALSE | Kick-off meeting scheduled next week.
T015 | Audit Internal Expense Reports | Finance | Emily Davis | 2025-09-29 | 2025-10-04 | 5 | Not Started | TRUE | Waiting for submission of all departmental reports.
Formulas:
Overdue? = AND(Table1[[#This Row],[Status]]<>"Completed",Table1[[#This Row],[Due Date]]<TODAY())
TASK MANAGEMENT TRACKER
Completed
7
Not Started
2
Total Tasks
15
In progress
6
Overdue Tasks
8

## Support Sheet
Status | Count | Owners | Count | Team | Count | Overdue
Completed | 7 | Sarah Johnson | 6 | Finance | 4 | 8
In Progress | 6 | David Kim | 3 | Strategy | 6
Not Started | 2 | James Miller | 1 | HR | 4
Total | 15 | Alex Chen | 2 | Marketing | 1
|  | Emily Davis | 3